## Planner
Cutover data readiness checklist
SAP S/4HANA migration cockpit ¦ Eleven checks per migration object, run before the first mock load
PostNow.ai ¦ SAP data automation, from days to minutes. ¦ postnow.ai
One row per check per object. Eleven checks are pre-filled for three objects as a worked example. Copy the block for every object in scope. Run this before the first mock load, not after it.
# * | Tier * | Migration Object * | Readiness Check * | Category | Evidence | Owner * | Status * | Date | Notes
1 | Master data | Material | Target definition confirmed before extract | Scope |  | MM Data Lead | Complete | 20260601
2 | Master data | Material | Required fields confirmed for the object | Scope |  | MM Data Lead | Complete | 20260601
3 | Master data | Material | Source field to target field mapping complete | Mapping |  | MM Data Lead | Complete | 20260601
4 | Master data | Material | Transformation rules written and agreed | Mapping |  | MM Data Lead | In progress
5 | Master data | Material | Every mapping task confirmed in the cockpit | Mapping |  | MM Data Lead | Complete | 20260601
6 | Master data | Material | Reference values validated against the target | Data quality |  | MM Data Lead | Complete | 20260601
7 | Master data | Material | Formats and leading zeros checked | Data quality |  | MM Data Lead | Complete | 20260601
8 | Master data | Material | Duplicate handling agreed before load | Data quality |  | MM Data Lead | In progress
9 | Master data | Material | Internal or external number range confirmed | Number ranges |  | MM Data Lead | Complete | 20260601 | Grouping uses internal numbering, so supplied numbers will not be kept. Confirm at reconciliation.
10 | Master data | Material | Reconciliation compares counts and identifiers | Reconciliation |  | MM Data Lead | Complete | 20260601
11 | Master data | Material | Owner assigned to every exception | Ownership |  | MM Data Lead | Complete | 20260601
12 | Master data | Business Partner (Customer) | Target definition confirmed before extract | Scope |  | MM Data Lead | In progress
13 | Master data | Business Partner (Customer) | Required fields confirmed for the object | Scope |  | MM Data Lead | Complete | 20260601
14 | Master data | Business Partner (Customer) | Source field to target field mapping complete | Mapping |  | MM Data Lead | Complete | 20260601
15 | Master data | Business Partner (Customer) | Transformation rules written and agreed | Mapping |  | MM Data Lead | Complete | 20260601
16 | Master data | Business Partner (Customer) | Every mapping task confirmed in the cockpit | Mapping |  | MM Data Lead | In progress
17 | Master data | Business Partner (Customer) | Reference values validated against the target | Data quality |  | MM Data Lead | Complete | 20260601
18 | Master data | Business Partner (Customer) | Formats and leading zeros checked | Data quality |  | MM Data Lead | Complete | 20260601
19 | Master data | Business Partner (Customer) | Duplicate handling agreed before load | Data quality |  | MM Data Lead | Complete | 20260601
20 | Master data | Business Partner (Customer) | Internal or external number range confirmed | Number ranges |  | MM Data Lead | In progress |  | Bank object must load first or these rows reject with a missing bank key.
21 | Master data | Business Partner (Customer) | Reconciliation compares counts and identifiers | Reconciliation |  | MM Data Lead | Complete | 20260601
22 | Master data | Business Partner (Customer) | Owner assigned to every exception | Ownership |  | MM Data Lead | Complete | 20260601
23 | Organisational | Cost Center | Target definition confirmed before extract | Scope |  | CO Data Lead | Complete | 20260601
24 | Organisational | Cost Center | Required fields confirmed for the object | Scope |  | CO Data Lead | In progress
25 | Organisational | Cost Center | Source field to target field mapping complete | Mapping |  | CO Data Lead | Complete | 20260601
26 | Organisational | Cost Center | Transformation rules written and agreed | Mapping |  | CO Data Lead | Complete | 20260601
27 | Organisational | Cost Center | Every mapping task confirmed in the cockpit | Mapping |  | CO Data Lead | Complete | 20260601
28 | Organisational | Cost Center | Reference values validated against the target | Data quality |  | CO Data Lead | In progress
29 | Organisational | Cost Center | Formats and leading zeros checked | Data quality |  | CO Data Lead | Complete | 20260601
30 | Organisational | Cost Center | Duplicate handling agreed before load | Data quality |  | CO Data Lead | Complete | 20260601
31 | Organisational | Cost Center | Internal or external number range confirmed | Number ranges |  | CO Data Lead | Complete | 20260601
32 | Organisational | Cost Center | Reconciliation compares counts and identifiers | Reconciliation |  | CO Data Lead | In progress
33 | Organisational | Cost Center | Owner assigned to every exception | Ownership |  | CO Data Lead | Complete | 20260601
Note on D5: The check being made. One row per check per object.
Note on F5: Where the proof lives. A file name, a ticket, a sign-off email.
Note on G5: The role that owns this field. Replace with a person in your own project.
Note on I5: YYYYMMDD.

## How to use
How to use this workbook
| 1. Copy the block per object | Eleven checks per object. The three objects here are a worked example, not the scope.
| 2. Record evidence, not opinion | A file name, a ticket number or a sign-off email. 'Done' is not evidence.
| 3. Run it before the first mock | The point is to find problems on paper. A checklist completed after the mock load has not saved anybody anything.
| 4. Filter on Blocked before cutover | Nothing goes into the cutover window while a check is Blocked.
| 5. Keep it as the audit record | This is the document you will be asked for after go-live.
Notes
Number ranges deserve explicit treatment. A supplied identifier may be accepted while the target assigns a different one, depending on internal or external numbering.
Validating rows against the live SAP system before a mock load shortens the correction cycle, because formatting and reference issues are found before the data reaches a cockpit template.
SAP documents dependencies object by object, so each project derives its own sequence and its own checks from the object documentation.
Load the finished data with PostNow.ai ¦ Start your 14 day free trial