## Planner
Migration object load sequence planner
SAP S/4HANA migration cockpit ¦ Plan the load order, track each object through mock loads to cutover
PostNow.ai ¦ SAP data automation, from days to minutes. ¦ postnow.ai
One row per migration object. Mandatory columns carry a dark green heading and an asterisk, and turn red if left blank. The Depends On column is the one that earns its keep: a dependency found during execution usually means a re-run.
Wave * | Tier * | Migration Object * | SAP Area | Depends On | Transfer Route | Owner * | Source System | Est. Volume | Mock 1 | Mock 2 | Cutover | Notes
1 | Foundational | Bank | FI |  | File upload | FI Data Lead | ECC PRD | 420 | Pass | Pass |  | Load before customers and suppliers or bank key errors follow.
1 | Foundational | G/L Account | FI |  | File upload | FI Data Lead | ECC PRD | 1,840 | Pass | Pass |  | Chart of accounts mapping confirmed with finance.
1 | Foundational | Enterprise structure | FI |  | Configuration | CO Data Lead | Design doc |  | Pass | Pass |  | Configured, not migrated. Tracked here for sequencing only.
2 | Organisational | Cost Center | CO | Enterprise structure | File upload | CO Data Lead | ECC PRD | 640 | Pass | Fail |  | Mock 2 failed on a profit centre not yet created.
2 | Organisational | Profit Center | CO | Enterprise structure | File upload | CO Data Lead | ECC PRD | 180 | Pass | Pass |  | Must precede material master.
3 | Master data | Material | MM | Profit Center, Cost Center | Staging tables | MM Data Lead | ECC PRD | 48,200 | Fail | Pass |  | Split into four files by material type. Volume drives the split.
3 | Master data | Business Partner (Customer) | SD | Bank | Staging tables | MM Data Lead | ECC PRD | 12,400 | Pass | Pass |  | Confirm BP grouping number range before cutover. See the checklist.
3 | Master data | Business Partner (Supplier) | MM | Bank | Staging tables | MM Data Lead | ECC PRD | 6,900 | Pass | Pass
3 | Master data | Bill of Material | PP | Material | File upload | MM Data Lead | ECC PRD | 9,100 | Fail | Pass |  | Mock 1 failed on components not yet loaded.
4 | Transactional | Open Purchase Order | MM | Material, Supplier | File upload | SD Data Lead | ECC PRD | 3,200 | Pass | Pass |  | Open quantity only, not history.
4 | Transactional | Open Sales Order | SD | Material, Customer | File upload | SD Data Lead | ECC PRD | 2,750 | Pass | Pass
4 | Transactional | G/L Open Item | FI | G/L Account, Cost Center | File upload | FI Data Lead | ECC PRD | 21,600 | Pass | Pass |  | Reconcile to trial balance before sign-off.
4 | Transactional | Inventory Balance | MM | Material | File upload | SD Data Lead | ECC PRD | 34,800 | Pass | Pass |  | Freeze physical movement during the cutover window.
Note on A5: Which load wave this object belongs to. 1 is the first.
Note on B5: Foundational, Organisational, Master data or Transactional.
Note on C5: The SAP migration object name as it appears in the cockpit.
Note on D5: FI, CO, MM, SD, PP, PM, HR.
Note on E5: Objects that must load first. This column is why the planner exists.
Note on F5: File upload, staging tables or direct transfer.
Note on G5: The role that owns this object. Replace with a person in your own project.
Note on I5: Row count you expect. Drives file splitting.
Note on J5: Result of the first mock load.

## How to use
How to use this workbook
| 1. List every object in scope | One row per migration object. Include objects that are configured rather than migrated, so the sequence is complete.
| 2. Assign the tier | Foundational, then Organisational, then Master data, then Transactional. The tier sets the broad order.
| 3. Fill Depends On | Name the objects that must exist first. This is where sequencing problems get found on paper instead of in a mock load.
| 4. Name one owner | The samples use role labels. Replace them with a named person, one per object. Shared ownership is how exceptions go unclaimed.
| 5. Record every mock | Pass, Fail or Partial per mock load. A Fail with no note is not useful, so write what failed in Notes.
| 6. Sign off at cutover | The Cutover column is the record you will be asked for afterwards.
Notes
SAP documents dependencies object by object rather than publishing one master load order, so this planner is where your project's own sequence gets written down.
Volume matters because template file size limits are documented in megabytes. Large objects are split into several files, and the split is planned here.
If customers load before bank master data, rows are rejected with missing bank key errors. Profit centre data must load before material master.
Load the finished data with PostNow.ai ¦ Start your 14 day free trial